# HybridRAG V2 — Sprint Plan (4-Week Demo Target)

Author: Jeremy Randall (CoPilot+)

Repo: HybridRAG_V2

Date: 2026-04-04 MDT

Demo Target: 2026-05-02 (4 weeks from today)

Work Mode: Nights and weekends included. Agile — get something useful out for demo ASAP.

## Guiding Principles

**Every sprint produces a working, demo-able system.** No big bang.

**Sprint 1 is the MVP.** If we only finish Sprint 1, we still have something better than V1.

**Reuse V1 code aggressively.** Parsers, GUI aesthetic, security modules — copy, don't rewrite.

**500 lines per class max** (comments excluded). Keeps code AI-reviewable and modular.

**Golden eval from day one.** 5 queries in Sprint 1, 20+ by Sprint 4.

## Sprint 1: Foundation (Week 1 — April 5-11)

Goal: Basic semantic query pipeline working against imported V1 index. Prove the repo boots, queries, and answers.

### Slice 1.1: Repo Bootstrap (Day 1-2)

Initialize git repo, CoPilot+.md, .gitignore

Create directory structure (src/, tests/, docs/, scripts/, config/)

Port Pydantic config schema from V1 (simplified: 1 mode, 2 presets)

Write config.yaml (single config, no mode switching)

Boot sequence: validate config → connect stores → ready

### Slice 1.2: LanceDB Store (Day 2-3)

Implement `lance_store.py` — create/open LanceDB table

Write `migrate_v1_index.py` script — import V1 FAISS vectors + SQLite chunks into LanceDB

Verify: 27.6M chunks loaded, vector search returns results

Verify: BM25 full-text search works (should be sub-second vs V1's 12-24s)

**Fallback if LanceDB waiver blocked:** implement `faiss_store.py` wrapping V1's FAISS + FTS5

### Slice 1.3: Basic Query Pipeline (Day 3-5)

Implement `llm/client.py` — unified openai SDK client (GPT-4o, GPT-OSS-120B)

Implement `query/vector_retriever.py` — LanceDB hybrid search (vector + BM25 + RRF)

Implement `query/reranker.py` — FlashRank reranking (top-30 → top-10)

Implement `query/context_builder.py` — assemble context from ranked chunks

Implement `query/generator.py` — GPT-4o generation with graduated confidence

Implement `api/routes.py` — POST /query endpoint

**Fallback if FlashRank waiver blocked:** use LanceDB built-in reranking

### Slice 1.4: First Golden Eval (Day 5-7)

Write 5 golden queries (mix of semantic, entity, aggregation)

Run eval, measure: fact_score, confidence accuracy, latency

Compare against V1 baseline on same queries

Document results

### Sprint 1 Exit Criteria

Repo boots from clean install in <30 seconds

Simple semantic queries return relevant answers with citations

LanceDB hybrid search under 100ms (vs V1's 12-24s FTS5)

FlashRank reranking under 50ms

5/5 golden queries produce reasonable answers

API endpoint functional

Sprint 1 Deliverable: A working RAG system that is already faster than V1 on keyword search, with FlashRank reranking and graduated confidence. No entity extraction yet — that's Sprint 2.

## Sprint 2: Quality-Gated Extraction (Week 2 — April 12-18)

Goal: Populate structured tables with validated entities. Make aggregation and lookup queries work.

### Slice 2.1: Entity Extraction Pipeline (Day 1-3)

Implement `ingest/entity_extractor.py` — GLiNER2 first-pass NER

Implement GPT-4o second-pass for complex entities (failure narratives, relationships)

Define entity schema: part_number, person, site, date, failure_mode, action_type

Run extraction on sample of 1,000 chunks, measure quality

**Fallback if GLiNER waiver blocked:** GPT-4o handles all extraction

### Slice 2.2: Quality Gates + Normalization (Day 2-4)

Implement `ingest/quality_gate.py` — confidence thresholds (reject < 0.7)

Implement `ingest/entity_normalizer.py` — controlled vocabulary matching

Build site vocabulary (25 IGS sites with known aliases)

Build part number pattern validator (ARC-NNNN, IGSI-NNNN, PO-YYYY-NNNN)

Build person name deduplication (separate phone/email from name)

Implement `scripts/audit_extraction.py` — quality report

### Slice 2.3: Structured Stores (Day 3-5)

Implement `store/entity_store.py` — SQLite tables for validated entities

Implement `store/relationship_store.py` — entity-relationship triples

Implement `store/table_store.py` — Docling-extracted table rows

Implement `ingest/table_extractor.py` — Docling table extraction

**Fallback if Docling waiver blocked:** openpyxl for .xlsx, pdfplumber for PDF tables

### Slice 2.4: Query Router + Structured Retrieval (Day 5-7)

Implement `query/router.py` — GPT-4o query classification

Implement `query/entity_retriever.py` — SQLite entity/aggregation lookup

Implement `query/table_retriever.py` — Text2SQL via GPT-4o

Implement `query/decomposer.py` — sub-query generation for COMPLEX queries

Run extraction on full corpus (background, may take 2-3 days)

### Sprint 2 Exit Criteria

Entity extraction produces validated, normalized data

"Who is the POC for Thule?" returns a real person name

"How many maintenance service reports in 2025?" returns a count from SQL

Quality audit report shows extraction accuracy metrics

10/10 golden queries passing (including entity + aggregation types)

Sprint 2 Deliverable: The structured extraction pipeline is live. Aggregation queries that were impossible in V1 now return SQL-backed answers with citations.

## Sprint 3: Query Intelligence + GUI (Week 3 — April 19-25)

Goal: Multi-hop queries, contextual enrichment integration, GUI with streaming, CRAG verification.

### Slice 3.1: Contextual Enrichment Integration (Day 1-2)

Import contextually-enriched chunks from EmbedEngine (phi4:14B output)

Load enriched text into LanceDB BM25 index

Measure retrieval improvement on golden queries (target: 30%+ improvement)

If EmbedEngine enrichment not ready: run enrichment via GPT-OSS (free) in batch

### Slice 3.2: Advanced Query Features (Day 2-4)

Multi-hop query support via relationship JOINs

Query expansion (synonym matching, acronym resolution)

Parent chunk expansion (retrieve child, return parent for context)

CRAG verification loop (GPT-OSS-20B grades response, retries if low confidence)

Streaming response support (SSE via FastAPI)

### Slice 3.3: GUI Port (Day 4-6)

Port V1 Tkinter color scheme, fonts, button styles

Implement streaming token display

Add query path badge (SEMANTIC / SQL / LOOKUP / MULTI-HOP)

Add graduated confidence indicator (HIGH green / PARTIAL yellow / NOT_FOUND red)

Add expandable source citations panel

Add structured results display (tables rendered as tables)

Remove: mode toggle, role selector, grounding bias slider

### Slice 3.4: Expanded Golden Eval (Day 6-7)

Expand golden eval to 20+ queries

Include all five failure classes: aggregation, entity, tabular, synonym, cross-doc

Measure: fact_score, confidence accuracy, latency, path routing accuracy

Compare V1 vs V2 on identical queries — document improvements

### Sprint 3 Exit Criteria

GUI boots and renders with V1 aesthetic

Streaming responses work end-to-end

Multi-hop queries produce merged results from multiple stores

CRAG verification catches at least 1 hallucination in eval set

15/20 golden queries passing with correct confidence levels

Sprint 3 Deliverable: A polished query system with GUI, streaming, and all five query types working. This is the minimum demo-ready system.

## Sprint 4: Demo Hardening (Week 4 — April 26 - May 2)

Goal: Production-quality on real work data. Demo-ready.

### Slice 4.1: Full Corpus Validation (Day 1-3)

Run full extraction on production corpus (if not completed in Sprint 2)

Validate extraction quality on work data (not Beast test data)

Tune: confidence thresholds, retrieval depths, RRF weights, reranking top-N

Build index audit report ("what did we extract?")

Identify and fix any corpus-specific edge cases

### Slice 4.2: Performance Tuning (Day 3-5)

Benchmark all query types on production data

Target: P50 < 3s, P95 < 10s

Optimize LanceDB index settings for 27.6M chunks

Optimize SQLite indexes for entity/aggregation queries

Memory profiling on Beast and laptop

### Slice 4.3: Demo Prep (Day 5-7)

Prepare 10 demo queries covering all failure classes

Document expected answers for each demo query

Rehearse demo flow: simple → entity → aggregation → tabular → complex

Build "V1 vs V2" comparison slides (same query, different results)

Final golden eval: 20/20 queries passing

Bug fixes, edge cases, polish

### Slice 4.4: Documentation + Handover (Day 7)

Update all docs with final architecture

Write deployment guide (clean install steps)

Write operator guide (how to run queries, read confidence levels)

Create demo script with talking points

### Sprint 4 Exit Criteria

20/20 golden queries passing on production data

P50 latency < 3s, P95 < 10s

GUI demo flow rehearsed and documented

Clean install works on fresh machine

All docs current

Sprint 4 Deliverable: Demo-ready system. V1 vs V2 comparison documented. Operator guide written. Ready to show.

## Risk Mitigation

Risk  |  Probability  |  Impact  |  Mitigation

Waiver delays (any of 4 packages)  |  Medium  |  Low  |  Every package has a fallback using approved software. Development proceeds.

GLiNER extraction quality poor on corpus  |  Medium  |  Medium  |  GPT-4o handles complex entities. Quality gates reject garbage. Audit report surfaces issues early.

LanceDB issues at 27.6M scale  |  Low  |  High  |  FAISS + FTS5 fallback is V1's proven stack. Migration script works both ways.

Full corpus extraction takes > 3 days  |  Medium  |  Low  |  Start in Sprint 2, runs in background. Demo can use partial extraction.

EmbedEngine enrichment not ready  |  Medium  |  Low  |  Run enrichment via GPT-OSS in batch. Same technique, API cost instead of free.

Demo date pressure  |  High  |  High  |  Sprint 1 alone produces a working system better than V1. Each subsequent sprint adds capability.

## Reuse from V1

V1 Module  |  V2 Reuse  |  Notes

32 file parsers  |  Copy as-is  |  Battle-tested on 100K+ files

GUI color scheme + buttons  |  Port aesthetic  |  Same Tkinter, simplified internals

Config validation pattern  |  Adapt to Pydantic  |  Simpler (1 mode, 2 presets)

Security/injection guard  |  Copy as-is  |  V1's 9-rule prompt is proven

Cost tracker  |  Copy as-is  |  Same openai SDK billing

Query history logging  |  Adapt  |  Same SQLite pattern

Boot sequence pattern  |  Adapt  |  Simpler (no mode detection)

EmbedEngine modules  |  Separate repo  |  Chunker, embedder, batch manager reused

Jeremy Randall | HybridRAG_V2 | 2026-04-04 MDT