## Metadata
Marker | [CANARY-VALIDATION-DOCUMENT-DO-NOT-USE-IN-PRODUCTION]
Canary Namespace | VALCAN-2026
Canary Document ID | VALDOC-005
Canary Bundle | 10_PROGRAM_MANAGEMENT
Synthetic Owner | Jane Canary
Production Use | prohibited
Title | Validation CDRL Status Register Q4 2024
Generated For | Task 18 canary pack authoring

## cdrl_status
Deliverable ID | Title | Status | Due date | Actual date | Owner | Contract
VAL-A001-KICKOFF-MINUTES | Kickoff minutes | COMPLETE | 2024-01-12 | 2024-01-11 | Jane Canary | VALCON-2024-0001
VAL-A005-SITE-SURVEY | Site survey package | COMPLETE | 2024-02-15 | 2024-02-14 | Pat Validation | VALCON-2024-0001
VAL-A009-MSR-Q4 | Quarterly maintenance service report | LATE | 2024-10-15 | 2024-10-22 | Pat Validation | VALCON-2024-0001
VAL-A012-TRAINING-SLIDES | Operator training slides | COMPLETE | 2024-03-10 | 2024-03-08 | Jane Canary | VALCON-2024-0001
VAL-A015-SPARES-LIST | Spare parts list | ON TRACK | 2024-04-05 | 2024-04-05 | John Testsubject | VALCON-2024-0001
VAL-A020-CYBER-BASELINE | Cyber baseline summary | COMPLETE | 2024-05-14 | 2024-05-13 | Riley Audit | VALCON-2024-0002
VAL-A027-POAM-UPDATE-Q4 | Quarterly POAM update | LATE | 2024-10-20 | 2024-10-28 | Riley Audit | VALCON-2024-0002
VAL-A031-IMS-REV-B | Integrated master schedule revision B | LATE | 2024-09-30 | 2024-10-04 | Jane Canary | VALCON-2024-0001
VAL-A040-CALIBRATION-ROLLUP | Calibration rollup | ON TRACK | 2024-08-16 | 2024-08-16 | John Testsubject | VALCON-2024-0001
VAL-A044-SHIPMENT-STATUS | Shipment status update | COMPLETE | 2024-07-19 | 2024-07-18 | John Testsubject | VALCON-2024-0001
VAL-A050-SCAN-COVERAGE | Scan coverage report | ON TRACK | 2024-11-08 | 2024-11-08 | Riley Audit | VALCON-2024-0002
VAL-A055-INVENTORY-ROLLUP | Inventory rollup | LATE | 2024-11-15 | 2024-11-21 | Morgan Ledger | VALCON-2024-0001