## Metadata
Marker | [CANARY-VALIDATION-DOCUMENT-DO-NOT-USE-IN-PRODUCTION]
Canary Namespace | VALCAN-2026
Canary Document ID | VALDOC-006
Canary Bundle | 10_PROGRAM_MANAGEMENT
Synthetic Owner | Jane Canary
Production Use | prohibited
Title | Validation Integrated Master Schedule Q4 2024
Generated For | Task 18 canary pack authoring

## ims
Milestone ID | Title | Planned | Actual | Status
VALMIL-001 | Kickoff complete | 2024-01-12 | 2024-01-11 | ON TIME
VALMIL-002 | Site surveys complete | 2024-02-16 | 2024-02-14 | ON TIME
VALMIL-003 | Spare kit staging | 2024-04-15 | 2024-04-24 | SLIPPED
VALMIL-004 | Q2 shipment gate | 2024-06-21 | 2024-06-28 | SLIPPED
VALMIL-005 | Cyber baseline complete | 2024-07-10 | 2024-07-18 | SLIPPED
VALMIL-006 | Calibration sweep complete | 2024-08-30 | 2024-08-29 | ON TIME
VALMIL-007 | Readiness dashboard review | 2024-10-10 | 2024-10-10 | ON TIME
VALMIL-008 | Q4 closeout package | 2024-12-18 | 2024-12-18 | ON TIME