## Metadata
Marker | [CANARY-VALIDATION-DOCUMENT-DO-NOT-USE-IN-PRODUCTION]
Canary Namespace | VALCAN-2026
Canary Document ID | VALDOC-009
Canary Bundle | 10_PROGRAM_MANAGEMENT
Synthetic Owner | Jane Canary
Production Use | prohibited
Title | Validation Budget Rollup FY2024
Generated For | Task 18 canary pack authoring

## budget_rollup
Contract or Category | Planned USD | Actual USD | Variance USD | Comment
VALCON-2024-0001 | 650000 | 612400 | -37600 | Lower travel and faster field closeout
VALCON-2024-0002 | 210000 | 198600 | -11400 | Lower exception-handling spend
Spare parts | 185000 | 192800 | 7800 | High-value Q2 buys absorbed by replan
Field service labor | 144000 | 138500 | -5500 | One deferred support week
Cyber remediation | 96000 | 92400 | -3600 | Two open POAM items carried to Q1 2025